## Sheet1
Checklist Skybot Web Portal
1. The portal should have fast, stable and secure web hosting that can work with enough visitors
1.1 Find the top 10 international hosting companies
1.2 Find out what uptime they guarantee
1.3 Investigate their server response (Time to First Byte (TTFB))
1.4 Check if they have 24/7 support
1.5 Provide the client with a list of hosts with uptime >=99.999%, TTFB <= 200ms, technical support 24/7 and rates.
2. A mobile version of the portal or a mobile application that can work quickly on mobile devices
2.1 To arrange meeting with back-end developers team
2.2 Find out if we can provide solutions for smart watches. (hold a meeting with developers)
2.3 Find out if we can simultaneously develop a mobile application and a web portal
2.4 Find out if the portal would have problems with the Safari browser or require additional resources/solutions to support it
2.5 Find out if we can optimize the portal/mobile app to open on mobile devices in less than 2 seconds in stable 4G/5G coverage areas. We take as a basis the parameters of the TTFB hoster <= 200ms
3. Convenient and clear design and the possibility of updating it
3.1 To arrange meeting with front-end developers team
3.2 Find out if we can make a minimalistic, but functional enough design.
3.3 Find out if we can quickly update it if requirements changed
3.4 Find out what "all modern browsers" are and create a pool of the 5 most used
3.5 Find out if we need to adapt the portal for each browser from the point above
4. Stable operation of the front end of the portal
4.1 Find out if we can quickly update all the elements of portal either web portal or mobile app.
4.2 Find out if we can quickly update content on portal in peak hours
4.3 Find out what will be faster and cheaper in terms of resources: integrate our YouTube chanel support so that users upload videos themselves and provide only a link to it, or create our own video upload form
4.4 Find out which formats are better to allow. To limit the possibility of adding photos in chosen formats.
5. Reliable work of the backend of the portal
5.1 see paragraph 1
5.2 find out what time is better to make portal system updates and how updates will affect the work of the portal
5.3 clarify the advantages and disadvantages of a one-level database and a three-level database
5.4 find out the number of transactions in the database that business analysts expect. Based on these data, provide recommendations on the frequency of backups
5.5 find out if our team has a tester with the education of a database administrator. If so, can he/she be transferred from testing to portal database support
6. Fast process of placing an order
6.1 find out which fields should be in the quick order form by phone number
6.1.1 find out if we can implement the pull-up of all data of already registered users by phone number
6.2 find out which fields should be in the standard order form
6.3 find out how to implement a feedback form if the customer has a problems with registration
7. User safety and secure payments
7.1 clarify the requirements for the business/hoster/database/developers to store payment card data in the online store database
7.2 clarify the difference between data transfer protocols of internet pages.
7.3 explain to the customer that the business cannot use non-encrypted methods of data transmission
7.4 find out if we can integrate different payment systems in addition to the standard checkout form
8. Information about each model of electric transport with a detailed description
8.1 find out which fields should be included in the product description for standardization
8.2 find out if we can use, to save resources, one feedback form during registration and/or for providing information about technical errors in product description.
8.3 find out if we can implement the possibility when the user themself corrects the error in the description. Maybe with a premoderation
9. Possibility to sign up for a test drive from the portal
9.1 to check with the legal team what information the user should provide in order to sign up for a test drive. Is it possible to implement it only by phone number?
9.2 to check with legal team if we need a form for a driver's license to sign up for a test drive
9.3 to check with legal team what information should be provided if person under the age of 13 wants to do test-drive of electric bicycle for example
10. The possibility of registering in the service center of those users who have already purchased the product (model)
10.1 find out what information should be provided in the warranty support form
10.1.1 how to verify that the product was purchased on our portal?
10.2 find out the possibility of implementing a quick appointment form for a non-guaranteed service by phone number
10.2.1 What information should be provided in the form of a quick appointment?
10.3 how to verify customers who bought product from us and who bought product from competitors?
11. Product reviews
11.1 consult with the marketing department in what form it is better to make a feedback system
11.2 who can leave product reviews?
11.2.1 registered buyer who bought the product?
11.2.2 registered buyer who did not buy the product?
11.3 how will the product rating be formed? stars or just negative/positive feedback?
11.4 Who can leave questions about the product?
11.4.1 registered buyer who bought the product?
11.4.2 registered buyer who did not buy the product?
11.4.3 unregistered buyer who did not buy the product?
12. Individual product recommendations
12.1 consult with the marketing department which client will receive which personal recommendations
12.2 Will personal recommendations be sent by phone or email?
12.3 implement the possibility to unsubscribe from the newsletter
13. Integration of the portal with video hosting for viewing video reviews of products (models)
13.1 analyze the leading video hosts for integration opportunities.
13.2 find out with the development teams the best practice of implementing video reviews of the product.
14. The portal should have the technical ability to implement analytics tools
14.1 what SEO tools does the customer want to use?
14.2 can we integrate these tools into the portal?
14.3 which of the developers will be responsible for cooperation with the customer's SEO and integration of additional analytics tools?
The check list is preliminary and may be changed after a meeting with the responsible personnel.